## Sheet1
Risk	Category	Probability	Impact (1 Lowest to 5 Highest)	RMMM	Risk Exposure
Problem Implementing Authentication Module	Schedule Risk	4.00%	2	Monitoring - Help catch problems early	0.04
Problem designing Mapping Module	Performance Risk	3.00%	5	Monitoring - Help catch problems early	0.15
Designed a product no one wants	Performance Risk	5.00%	5	Management - Talk with the product owners, consider redesigning product	0.25
Hardware Failure	Cost Risk/Schedule Risk	10.00%	3	Mitigation - Backup computers	0.3
Member of the team falls ill/drops out and is unable to work	Schedule Risk	10.00%	3	Management - Be able to recruit new members/have backups/delegate tasks effectively	0.3
Problem Implementing Notification Module	Schedule Risk	12.00%	3	Monitoring - Help catch problems early	0.36