## Sheet1
Needed Tasks |  |  | Tasks In Progress |  |  |  |  | Tasks Pending/Testing Needed | Completed Tasks
Task Name | Task Type | Multiple Members Advised? | Task Name | Task Type | Member(s) | Open to extra help? | Want outside testing? | Task Name | Task Name | Task Type | Member(s) | Tested By
Car Database/Scoring | Programming | Yes | [6 empty] | API Use | Programming | Nick
Leaderboards/User accounts | Programming | Yes | [6 empty] | Camera Use | Programming | Nick
[9 empty] | Create Android Application Launcher Icon | UI/Design | Nick | Not Needed
[9 empty] | GPS Tracking | Programming | Luke
[9 empty] | FireBase Implementation | Programming | Luke | Yes
[9 empty] | Figure out how FireBase works | Programming | Luke, Dan | Yes
[9 empty] | UI Sketches | UI | Cristina, Jenna
[9 empty] | UI implementation in Android Studio | UI | Cristina, Jenna
[9 empty] | Achievement/Trophies planning | Design | Jenna
[9 empty] | > List ideas for trophies | Design | Cristina | Yes
Feel free to add any tasks/subdivide the existing ones
If a task is marked "open to extra help", put your name along side theirs and get in contact to start collaborating.